## Template
LOFTHUS FRUKT OG SAFT |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: 11/11/2019 - Kristian Hovland |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
PREPARATION |  | 3 d
Assign Tasks | Project Manager | 1 d | bar: WEEK 1 M
Lists of products | Digital Marketer | 2 d | bar: WEEK 1 M to WEEK 1 T
Research | Front-end / Project Manager | 3 d | bar: WEEK 1 M to WEEK 1 W
DESIGN |  | 4 d
Meeting / Assing tasks | Project Manager | 1 d | bar: WEEK 1 W
Review branding information/materials | Project Manager | 1 d | bar: WEEK 1 W
Wireframe | Designer | 1 d | bar: WEEK 1 W
Design Pages | Designer | 3 d | bar: WEEK 1 W to WEEK 1 F
Photos | Project Manager | 1 d | bar: WEEK 1 F
Design email message | Designer | 1 d | bar: WEEK 1 F
Review/Approve design | Project Manager | 1 d | bar: WEEK 2 M
PRE-CODING |  | 1 d
Meeting about tasks | Project Manager | 1 d | bar: WEEK 1 TH
Prepare epics/features/user stories | Project Manager | 1 d | bar: WEEK 1 TH
Meeting about production/tools | Project Manager | 1 d | bar: WEEK 1 TH
CODING |  | 8 d
Home Page | Front-end | 2 d | bar: WEEK 2 M to WEEK 2 T
Feature - Webshop | Back-end | 3 d | bar: WEEK 2 M to WEEK 2 W
Contact Page | Front-end | 2 d | bar: WEEK 2 W to WEEK 2 TH
Feature - Live Chat | Back-end | 2 d | bar: WEEK 2 TH to WEEK 2 F
Product page with webshop | Front-end | 4 d | bar: WEEK 2 F; WEEK 3 M to WEEK 3 W
Feature - Product information | Designer | 2 d | bar: WEEK 2 TH to WEEK 2 F
Review/Approve Coding | Project Manager | 2 d | bar: WEEK 3 W
POST-CODING |  | 2 d
Debugging | Back-end | 1 d | bar: WEEK 3 TH
Testing | Front-end | 1 d | bar: WEEK 3 TH
Meeting Full Review | Project Manager | 1 d | bar: WEEK 3 TH
Meeting with client | Project Manager | 2 d | bar: WEEK 3 TH
Post-Meeting Changes | All | 2 d | bar: WEEK 3 TH to WEEK 3 F
Meeting with client | Project manager | 1 d | bar: WEEK 3 F
UPLOAD |  | 2 d
Meeting with client about dates/finished product | Project Manager | bar: WEEK 3 F
Upload finale product | Back-end | bar: WEEK 4 M
Transfer all files to the client | All | bar: WEEK 4 M
Premiere of the site | All | bar: WEEK 4 M
Review meeting | All | bar: WEEK 4 M
ANNOTATIONS |  |  | WEEK 4 TH: Project Manager
Front-end Developer
Graphic Designer
Back-end Developer
All the above
|  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2018 - StudioBinder

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
|  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder